## Sheet1
No | Function | Sub Function | Task description | Priority | Batch | Handle By | Target End Date | Start Date | Actual End Date | Status | Remarks | Estimate Man-day
1 | Public User Registration |  |  |  | 3
2 | Login System ( Login, Logout, reset password ...) |  |  |  | 3
3 | Forgot login ID, forgot Password |  |  |  | 3
4 | iAMSmart integration |  |  |  | 4
5 | Gov Payment Gateway Integration |  |  |  | 4
6 | Application Permission |  | Equal to role function setup and reflect to tree menu which is mentioned in item 48 and 49 | 17 | 2 | [5 empty] | Equal to role function setup and reflect to tree menu
7 | Notification System |  | It should divide into alert user or user group 2 days for creating a new function for another button/function store notification record 2 days for showing notification record in UI | 18 | 2 | Dillanxiong/Sonya | 2021-09-16 |  |  |  | It should divide into alert user or user group 2 days for creating a new function for another button/function store notification record 2 days for showing notification record in UI | 4
8 | Application Level Messaging system-internal communication |  |  |  | 5
9 | General Activity Log |  | Log the activity (Insert/Update/Delete/Submit/Approve/Reject ....) of the mentioned forms on left hand side in an activity log table. |  | 1
10 |  | User maintenace |  | 10 |  | Dillanxiong/Sonya | 2021-09-10 |  |  |  |  | 0.2
11 |  | Role maintenance |  | 11 |  | Dillanxiong/Sonya | 2021-09-10 |  |  |  |  | 0.2
12 |  | Group maintenance |  | 12 |  | Dillanxiong/Sonya | 2021-09-10 |  |  |  |  | 0.2
13 |  | Function maintenance |  | 13 |  | Dillanxiong/Sonya | 2021-09-10 |  |  |  |  | 0.2
14 |  | User role maintenance |  | 14 |  | Dillanxiong/Sonya | 2021-09-10 |  |  |  |  | 0.2
15 |  | User role group maintenance |  | 15 |  | Dillanxiong/Sonya | 2021-09-10 |  |  |  |  | 0.2
16 |  | Menu maintenance |  | 16 |  | Dillanxiong/Sonya | 2021-09-10 |  |  |  |  | 0.2
17 |  | MC maintenance tables (TBC)
18 |  | AML maintenance tables (TBC)
19 |  | FCL maintenance tables (TBC)
20 |  | ATCL maintenance tables (TBC)
21 | System Audit log |  | Create log table (E.g. PLIS_USER -> PLIS_USER_LOG) to store the system data changed. Log table should be the same table structure with original table. It is necesary append five fields list as following: ID(auto increment by DB) action (Insert/Update/Delete) updated_datetime update_by (User_ID) update_by_role (Role_ID) |  | 1
22 |  | User maintenace |  | 20 | 1 | Dillanxiong/Sonya | 2021-09-23 |  |  |  |  | 0.2
23 |  | Role maintenance |  | 21 | 1 | Dillanxiong/Sonya | 2021-09-23 |  |  |  |  | 0.2
24 |  | Group maintenance |  | 22 | 1 | Dillanxiong/Sonya | 2021-09-23 |  |  |  |  | 0.2
25 |  | Function maintenance |  | 23 | 1 | Dillanxiong/Sonya | 2021-09-23 |  |  |  |  | 0.2
26 |  | User role maintenance |  | 24 | 1 | Dillanxiong/Sonya | 2021-09-23 |  |  |  |  | 0.2
27 |  | User role group maintenance |  | 25 | 1 | Dillanxiong/Sonya | 2021-09-23 |  |  |  |  | 0.2
28 |  | Menu maintenance |  | 26 | 1 | Dillanxiong/Sonya | 2021-09-23 |  |  |  |  | 0.2
29 |  | MC maintenance tables (TBC) |  |  | 1
30 |  | AML maintenance tables (TBC) |  |  | 1
31 |  | FCL maintenance tables (TBC) |  |  | 1
32 |  | ATCL maintenance tables (TBC) |  |  | 1
33 | Worflow Engine & eForm integration |  | Study the following in the WorkFlowEngine 1)Feasibility to synchronize the field status_id of the table PLIS_Status to WorkFlowEngine process table. 2)Create a funtion passing the WorkFlowType (E.g. Initial AME/Renewal AME) and application status to show the dynamic graphic for checking application status. 3)Show the dynamic commands (action buttons) control in custom page | 14 | 1 | [6 empty] | 2
34 | Worflow engine instance control |  |  | 15 | 1
35 |  |  | Coding for MC (TBC)
36 |  |  | Coding for AML (TBC)
37 |  |  | Coding for FCL (TBC)
38 |  |  | Coding for ATCL (TBC)
39 | General Item Searching |  |  |  | 5
40 | Application Menu (Back end side) |  | 1) The menu should support base on login user role dynamically show the menu function. The menu detail please view the following document. https://docs.google.com/spreadsheets/d/1yxMjWkg6YKBsEgW6_X3euhtix8nanIMzImYgT7OWDMA/edit#gid=1493028765 | 1 | 1 | Dillanxiong/Sonya | 2021-08-30 |  |  |  |  | 2
41 | Master & Setting Maintenance |  |  |  | 2
42 |  | User Maintainence (in backend) | Insert/Update/Delete records in the table (Employee) of WorkFlowEngine system. | 2 | 2 | Dillanxiong/Sonya | 2021-09-02 |  |  |  |  | 2
43 |  | User Role Maintenance (in backend) | Insert/Update/Delete records in the table (EmployeeRole) of WorkFlowEngine system. | 3 | 2 | Dillanxiong/Sonya | 2021-09-02 |  |  |  |  | 2
44 |  | Role Maintenance (in backend) | Insert/Update/Delete records in the table (Roles) of WorkFlowEngine system. | 4 | 2 | Dillanxiong/Sonya | 2021-09-06 |  |  |  |  | 2
45 |  | Group Maintenance (in backend) |  | 5 | 2 | Dillanxiong/Sonya | 2021-09-06 |  |  |  |  | 1
46 |  | Function Maintenance (in backend) |  | 6 | 2 | Dillanxiong/Sonya | 2021-09-06 |  |  |  |  | 1
47 |  | User_Role_Group Maintenance (in backend) |  | 7 | 2 | Dillanxiong/Sonya | 2021-09-08 |  |  |  |  | 2
48 |  | Group Accessible Function Maintenance (in backend) | Function type 1) Menu item 2) Dashboard function 3) MC | 8 | 2 | Dillanxiong/Sonya | 2021-09-08 |  |  |  |  | 2
49 |  |  | Functions Type 4) ATCL (TBC) 5) AML (TBC) 6) FCL (TBC) |  | 2
50 |  | Employer Maintenance (in backend) |  | 9 | 2 | Dillanxiong/Sonya | 2021-09-09 |  |  |  |  | 1
51 | Backend login (in backend) |  | Dashboard implementation |  | 2
52 |  | MC |  | 19 | 2 | Dillanxiong/Sonya | 2021-09-22 |  |  |  |  | 4
53 |  | ATCL (TBC) |  |  | 2
54 |  | FCL (TBC) |  |  | 2
55 |  | AML (TBC) |  |  | 2
56 | 2 FA support for backend |  | All backend user must have 2FA verification when login the system | 27 | 2 | Dillanxiong/Sonya | 2021-09-27 |  |  |  |  | 2